## 📋 Overview
🤖 RoboNet — Project Tracker
Unified Robot Control · BLE · WiFi · CAN Bus · Qt6 · ESP-IDF
Phase 1 — Mobile BLE Control |  | Phase 2 — PC WiFi Control |  | Phase 3 — CAN Sensor Network
Steps total |  | Steps total |  | Steps total
Done |  | Done |  | Done
Technology Stack
Technology | What You Learn | Phase | Module / Library | Status | Notes
Qt 6 Mobile (Android) | QML UI, Qt Sensors, Qt Bluetooth, BLE client | Phase 1 | QtSensors, QtBluetooth | 🔄 In Progress | arm64-v8a ABI
Qt 6 Desktop (PC) | Widgets/QML, QTcpSocket, network control | Phase 2 | QtNetwork, QtWidgets | ⏳ Planned
Bluetooth Low Energy | GATT profiles, custom services, notifications | Phase 1 | NimBLE (ESP-IDF) | 🔄 In Progress
ESP-IDF Firmware | FreeRTOS tasks, peripherals, NVS, drivers | 1,2,3 | ESP-IDF v5.x | 🔄 In Progress
WiFi / TCP | Station mode, TCP server, command parsing | Phase 2 | esp_wifi, lwip | ⏳ Planned
CAN Bus | Multi-node network, arbitration, framing | Phase 3 | TWAI driver (ESP-IDF) | ⏳ Planned | SN65HVD230 transceiver
I2C | MPU6050, Magnetometer, Humidity sensor | 1,3 | i2c_master (ESP-IDF) | ✅ Done | Already working on robot
Motor Control | PWM, direction logic, speed mapping | Phase 1 | MCPWM (ESP-IDF) | 🔄 In Progress

## 📗 Phase 1
Phase 1 — Mobile BLE Robot Control
# | Step Description | Status | Category | Priority | Notes / Output | Est. Hours
1 | Set up Qt 6 Android project in Qt Creator | ⬜ To Do | Qt Setup | 🔴 High | Enable QtSensors + QtBluetooth in CMakeLists | 2
2 | Read accelerometer data using QAccelerometer | ⬜ To Do | Qt Sensors | 🔴 High | QAccelerometerReading: x, y, z values | 2
3 | Calculate Roll and Pitch from accelerometer | ⬜ To Do | Qt Sensors | 🔴 High | atan2 formula, output in degrees | 1
4 | Build QML dashboard: display live Roll & Pitch | ⬜ To Do | Qt UI | 🔴 High | Gauges or arc indicators in QML | 3
5 | Add BLE scan UI: list nearby BLE devices | ⬜ To Do | Qt Bluetooth | 🔴 High | QBluetoothDeviceDiscoveryAgent | 3
6 | Connect to ESP32-S3 BLE server from Qt app | ⬜ To Do | Qt Bluetooth | 🔴 High | QLowEnergyController | 2
7 | Discover GATT service & characteristic on ESP32 | ⬜ To Do | Qt Bluetooth | 🔴 High | QLowEnergyService + characteristic UUID | 2
8 | Send Roll/Pitch string over BLE every 50ms | ⬜ To Do | Qt Bluetooth | 🔴 High | writeCharacteristic(), format: R:-12.5,P:8.3 | 2
9 | ESP32-S3: Create BLE GATT server with NimBLE | ⬜ To Do | ESP-IDF BLE | 🔴 High | Custom Service UUID + Writable Characteristic | 4
10 | ESP32-S3: Receive and parse Roll/Pitch over BLE | ⬜ To Do | ESP-IDF BLE | 🔴 High | on_write callback, sscanf or strtof parsing | 2
11 | ESP32-S3: Implement motor PWM with MCPWM | ⬜ To Do | ESP-IDF Motor | 🔴 High | 4-channel PWM, direction GPIO | 3
12 | Map Roll/Pitch angles to motor speed/direction | ⬜ To Do | ESP-IDF Motor | 🔴 High | Dead zone ±5°, proportional speed above 10° | 2
13 | End-to-end test: tilt phone → robot moves | ⬜ To Do | Integration | 🔴 High | Test all 4 directions + stop | 2
14 | Tune dead zones and response curves | ⬜ To Do | Tuning | 🟡 Medium | Add expo curve for smoother control | 1
15 | Add connection status indicator to Qt UI | ⬜ To Do | Qt UI | 🟡 Medium | Connected/Disconnected badge in QML | 1
Progress

## 📘 Phase 2
Phase 2 — PC WiFi Robot Control
# | Step Description | Status | Category | Priority | Notes / Output | Est. Hours
1 | Create Qt 6 Desktop project in Qt Creator | ⬜ To Do | Qt Setup | 🔴 High | QtNetwork + QtQuick or QtWidgets | 1
2 | Design D-pad control UI: F/B/L/R/Stop buttons | ⬜ To Do | Qt UI | 🔴 High | QML or QPushButton with key events | 2
3 | Implement TCP client in Qt: connect to ESP32 | ⬜ To Do | Qt Network | 🔴 High | QTcpSocket, target ESP32 IP + port 8080 | 2
4 | Send directional commands as text over TCP | ⬜ To Do | Qt Network | 🔴 High | FWD / BWD / LEFT / RIGHT / STOP strings | 1
5 | Add keyboard shortcuts (arrow keys) to PC app | ⬜ To Do | Qt UI | 🟡 Medium | QKeyEvent or Shortcut in QML | 1
6 | ESP32-S3: Add WiFi station mode (connect to router) | ⬜ To Do | ESP-IDF WiFi | 🔴 High | esp_wifi_init, SSID/password in menuconfig | 2
7 | ESP32-S3: Create TCP server on port 8080 | ⬜ To Do | ESP-IDF WiFi | 🔴 High | lwip sockets, accept() loop in FreeRTOS task | 3
8 | ESP32-S3: Parse TCP commands, call motor functions | ⬜ To Do | ESP-IDF WiFi | 🔴 High | Reuse motor_control from Phase 1 | 2
9 | Handle dual control: BLE + WiFi simultaneously | ⬜ To Do | Integration | 🔴 High | Priority logic: last command wins | 2
10 | Test PC buttons controlling robot over WiFi | ⬜ To Do | Integration | 🔴 High | All 5 commands on real hardware | 1
11 | Show robot IP address on Qt app (mDNS or static IP) | ⬜ To Do | Qt Network | 🟡 Medium | QZeroConf or fixed IP in settings | 2
12 | Add speed slider to PC app | ⬜ To Do | Qt UI | 🟢 Low | Scale motor PWM by 0–100% slider value | 1
Progress

## 📙 Phase 3
Phase 3 — CAN Sensor Network
# | Step Description | Status | Category | Priority | Notes / Output | Est. Hours
1 | Wire CAN bus: 3× ESP32-S3 + SN65HVD230 transceivers | ⬜ To Do | Hardware | 🔴 High | 120Ω termination resistors at both ends | 2
2 | ESP32-S3 Node A: Read humidity sensor over I2C | ⬜ To Do | ESP-IDF I2C | 🔴 High | DHT20 or SHT31 driver, read every 1s | 2
3 | Node A: Publish humidity data on CAN bus (ID 0x100) | ⬜ To Do | ESP-IDF CAN | 🔴 High | TWAI driver, 8-byte frame | 3
4 | ESP32-S3 Node B: Read switch inputs (GPIO) | ⬜ To Do | ESP-IDF GPIO | 🔴 High | Debounce in software, publish state on CAN | 2
5 | Node B: Control relay outputs (GPIO) | ⬜ To Do | ESP-IDF GPIO | 🔴 High | Receive CAN command → toggle relay | 2
6 | Node B: Publish relay + switch states on CAN (ID 0x200) | ⬜ To Do | ESP-IDF CAN | 🔴 High | Bitfield in payload byte | 2
7 | ESP32-S3 Node C: Receive all CAN frames | ⬜ To Do | ESP-IDF CAN | 🔴 High | Filter IDs 0x100 and 0x200 | 2
8 | Node C: Connect to WiFi, open TCP to PC | ⬜ To Do | ESP-IDF WiFi | 🔴 High | Station mode, reconnect on drop | 2
9 | Node C: Forward CAN data to PC as JSON over WiFi | ⬜ To Do | ESP-IDF WiFi | 🔴 High | {node:A, hum:65.2, temp:22.1} | 2
10 | Qt PC App: Add CAN dashboard tab | ⬜ To Do | Qt UI | 🔴 High | Humidity gauge, relay toggles, switch LEDs | 4
11 | Qt PC App: Receive and parse JSON from Node C | ⬜ To Do | Qt Network | 🔴 High | QJsonDocument parsing | 2
12 | Qt PC App: Send relay ON/OFF commands to Node C | ⬜ To Do | Qt Network | 🟡 Medium | Node C relays command to Node B via CAN | 2
13 | Add data logging to Excel/CSV from Qt app | ⬜ To Do | Qt Features | 🟢 Low | QFile + timestamped rows | 2
14 | End-to-end CAN test: all 3 nodes + PC dashboard | ⬜ To Do | Integration | 🔴 High | Verify all sensors, relays, and switches | 2
15 | Document CAN message table (IDs, payloads) | ⬜ To Do | Documentation | 🟡 Medium | Add to README / project docs | 1
Progress

## 🔧 Hardware
Hardware Inventory & Wiring Notes
Item | Qty | Role | Connection | Phase | Notes
4-Wheel Robot (B0CCNJKM17) | 1 | Mobile robot platform | — | 1,2 | Already assembled
ESP32-S3 (on robot) | 1 | BLE server + Motor controller | PWM → motor driver | 1,2
ESP32-S3 Node A | 1 | Humidity sensor node | I2C → sensor; CAN → Node C | 3
ESP32-S3 Node B | 1 | Relay + Switch node | GPIO → relays/switches; CAN | 3
ESP32-S3 Node C | 1 | CAN-WiFi Gateway | CAN in; WiFi out to PC | 3
Xiaomi Redmi Note 9 Pro | 1 | BLE controller (Qt mobile app) | BLE → Robot ESP32-S3 | 1 | arm64-v8a
PC (Windows) | 1 | Qt desktop controller + dashboard | WiFi/TCP → Robot; WiFi → Node C | 2,3
MPU6050 | 1 | IMU (already wired) | I2C on robot ESP32-S3 | 1 | Already working
Magnetometer | 1 | Compass (already wired) | I2C on robot ESP32-S3 | 1 | Already working
Character LCD | 1 | Display (already working) | I2C or parallel on robot | 1 | Already working
Humidity Sensor (DHT20/SHT31) | 1 | Humidity + temperature | I2C on Node A | 3
Relay Board (4-ch) | 1 | Output control | GPIO on Node B | 3 | 5V relay, logic-level trigger
Switches / Push buttons | 3+ | Digital inputs | GPIO on Node B | 3 | Pull-up resistors
SN65HVD230 CAN Transceiver | 3 | CAN physical layer | One per ESP32-S3 CAN node | 3 | 3.3V compatible
120Ω Resistors | 2 | CAN bus termination | At each end of CAN bus | 3